|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *10/19*  Aim 4.4 qPCR +  Milk Composition Analysis | *11/19*  Histology of MG Aim 4.1 | *12/19*  Paper Writing  Aim 4 | *1/20*  Potential GSI | *2/20*  GSI | *3/20*  GSI +  Placental KO achieved |
| *4/20*  GSI | *5/20*  Start Aim 1 Experiment | *6/20* | *7/20* | *8/20*  Data Complete for Aim 1 | *9/20*  qPCR + histology for Aim 1 |
| *10/20*  RNAseq for Aim 1 | *11/20*  Placental GR-KO Mating Aim 1.6 | *12/20* | *1/21* | *2/21*  Paper Writing  Aim 1 | *3/21*  Placental mTORC1 Mating Aim 3 |
| *4/21* | *5/21* | *6/21*  Data Complete for Aim 3 | *7/21*  Start Aim 2 Experiment | *8/21*  Paper Writing for Aim 3 | *9/21* |
| *10/21*  Data Complete for Aim 3 | *11/21* | *12/21*  Paper Writing  Aim 2 | *1/22* | *2/22* | *3/22*  ***Data Meeting*** |
| *4/22* | *5/22*  ***Graduation ☺*** |  |  |  |  |